## Expediting
Requisitioner | Requisition Date | Purchase Requisition | Purchasing Document | Item | Short Text | Order Quantity | Unit Price | Net Order Value | Still to be delivered (qty) | Vendor delivery date | ETA | Ubicación | Supplier
DQUIÑONEZ | 2023-08-05 | 12820041 | 4502852427 | 10 | MÁQ DE TERMOFUSIÓN MCELROY ROLLING 250 | 1 | 29055 | 29055 | 0 | 2023-08-31 | 2023-09-11 | WAREHOUSE | THIESSEN DEL PERU S.A.
DQUIÑONEZ | 2023-08-06 | 12820041 | 4502852427 | 20 | PIT BULL 26- CAPACIDAD PARA 2" IPS A 6" | 1 | 12150 | 12150 | 0 | 2023-08-31 | 2023-09-11 | WAREHOUSE | THIESSEN DEL PERU S.A.
DQUIÑONEZ | 2023-08-07 | 12820041 | 4502852427 | 30 | 12 DIPS HF 240,60,3 F/M PKG - ROLLING 41 | 1 | 55017 | 55017 | 1 | 2023-12-20 | 2023-10-25 | NO RECEPCIONADO | THIESSEN DEL PERU S.A.
DQUIÑONEZ | 2023-08-08 | 12820041 | 4502852427 | 40 | 10IPS INSERT SET | 1 | 2001 | 2001 | 0 | 2023-08-31 | 2023-09-11 | WAREHOUSE | THIESSEN DEL PERU S.A.
DQUIÑONEZ | 2023-08-09 | 12820041 | 4502852427 | 50 | 8IPS INSERT SET | 1 | 2001 | 2001 | 0 | 2023-08-31 | 2023-09-11 | WAREHOUSE | THIESSEN DEL PERU S.A.
DQUIÑONEZ | 2023-08-10 | 12820041 | 4502852427 | 60 | 6IPS MASTER INSERT SET | 1 | 3037 | 3037 | 0 | 2023-08-31 | 2023-09-11 | WAREHOUSE | THIESSEN DEL PERU S.A.
DQUIÑONEZ | 2023-08-11 | 12820041 | 4502852427 | 70 | 4IPS/100MM JIS INSERT SET | 1 | 853 | 853 | 0 | 2023-08-31 | 2023-09-11 | WAREHOUSE | THIESSEN DEL PERU S.A.
DQUIÑONEZ | 2023-08-12 | 12820041 | 4502852427 | 80 | 8"IPS/250MM MSTR INSR SET/PINS INSERTO | 1 | 2120 | 2120 | 0 | 2023-08-31 | 2023-09-11 | WAREHOUSE | THIESSEN DEL PERU S.A.
DQUIÑONEZ | 2023-08-13 | 12820041 | 4502852427 | 90 | 6IPS MASTER INSERT SET 801510 INSERTO | 1 | 1271 | 1271 | 0 | 2023-08-31 | 2023-09-11 | WAREHOUSE | THIESSEN DEL PERU S.A.
DQUIÑONEZ | 2023-08-14 | 12820041 | 4502852427 | 100 | 4IPS/100MM JIS INSERT SET INSERTO | 1 | 831 | 831 | 0 | 2023-08-31 | 2023-09-11 | WAREHOUSE | THIESSEN DEL PERU S.A.
DQUIÑONEZ | 2023-08-15 | 12820041 | 4502852427 | 110 | 3IPS INSERT SET INSERTO | 1 | 856 | 856 | 0 | 2023-08-31 | 2023-09-11 | WAREHOUSE | THIESSEN DEL PERU S.A.
DQUIÑONEZ | 2023-08-16 | 12820041 | 4502852427 | 120 | 2IPS INSERT SET INSERTO | 1 | 856 | 856 | 0 | 2023-08-31 | 2023-09-11 | WAREHOUSE | THIESSEN DEL PERU S.A.
DQUIÑONEZ | 2023-08-17 | 12820041 | 4502852427 | 130 | 4IPS/100MM JIS 2J INSERT SET | 1 | 414 | 414 | 0 | 2023-08-31 | 2023-09-11 | WAREHOUSE | THIESSEN DEL PERU S.A.
DQUIÑONEZ | 2023-08-18 | 12820041 | 4502852427 | 140 | 3IPS 2J INSERT SET | 1 | 424 | 424 | 0 | 2023-08-31 | 2023-09-11 | WAREHOUSE | THIESSEN DEL PERU S.A.
DQUIÑONEZ | 2023-08-19 | 12820041 | 4502852427 | 150 | 2IPS 2J INSERT SET | 1 | 401 | 401 | 0 | 2023-08-31 | 2023-09-11 | WAREHOUSE | THIESSEN DEL PERU S.A.
GBARDALEZ | 2023-08-20 | 13016079 | 4502882598 | 10 | TRACSTAR 618 | 1 | 88959 | 88959 | 0 | 2023-09-29 | 2023-10-05 | WAREHOUSE | THIESSEN DEL PERU S.A.
GBARDALEZ | 2023-08-21 | 13016079 | 4502882598 | 20 | HEATER DE 6 A 12" | 1 | 5809 | 5809 | 0 | 2023-09-29 | 2023-10-05 | WAREHOUSE | THIESSEN DEL PERU S.A.
GBARDALEZ | 2023-08-22 | 13016079 | 4502882598 | 30 | POLINES | 2 | 1631 | 3262 | 2 | 2023-10-25 |  | NO RECEPCIONADO | THIESSEN DEL PERU S.A.
GBARDALEZ | 2023-08-23 | 13016079 | 4502882598 | 40 | 16IPS INSERT SET | 1 | 4670 | 4670 | 0 | 2023-09-29 | 2023-10-05 | WAREHOUSE | THIESSEN DEL PERU S.A.
GBARDALEZ | 2023-08-24 | 13016079 | 4502882598 | 50 | 14 OD/355MM INSERT SET | 1 | 4670 | 4670 | 0 | 2023-09-29 | 2023-10-05 | WAREHOUSE | THIESSEN DEL PERU S.A.
GBARDALEZ | 2023-08-25 | 13016079 | 4502882598 | 60 | 12" IPS MASTER | 1 | 5652 | 5652 | 0 | 2023-09-29 | 2023-10-05 | WAREHOUSE | THIESSEN DEL PERU S.A.
GBARDALEZ | 2023-08-26 | 13016079 | 4502882598 | 70 | 10IPS INSERT SET | 1 | 1927 | 1927 | 0 | 2023-09-29 | 2023-10-05 | WAREHOUSE | THIESSEN DEL PERU S.A.
GBARDALEZ | 2023-08-27 | 13016079 | 4502882598 | 80 | 8IPS INSERT SET | 1 | 1927 | 1927 | 0 | 2023-09-29 | 2023-10-05 | WAREHOUSE | THIESSEN DEL PERU S.A.
GBARDALEZ | 2023-08-28 | 13016079 | 4502882598 | 90 | 6IPS MASTER INSERT SET | 1 | 2925 | 2925 | 0 | 2023-09-29 | 2023-10-05 | WAREHOUSE | THIESSEN DEL PERU S.A.
GBARDALEZ | 2023-08-29 | 13016079 | 4502882598 | 100 | DL 7 PKG - DATALOGGER N° 7 | 1 | 8199 | 8199 | 0 | 2023-09-29 | 2023-10-05 | WAREHOUSE | THIESSEN DEL PERU S.A.
GBARDALEZ | 2023-08-30 | 13016859 | 4502882607 | 10 | RESISTENCIA DE 120V DE IMPORTACIÓN | 1 | 483 | 483 | 0 | 2023-09-29 | 2023-10-02 | WAREHOUSE | THIESSEN DEL PERU S.A.
GBARDALEZ | 2023-08-31 | 13016859 | 4502882607 | 20 | HEATER COMPLETO DE 220V | 1 | 4689.7 | 4689.7 | 0 | 2023-08-31 | 2023-09-11 | PLATAFORMA J | THIESSEN DEL PERU S.A.
JMENDIVIL | 2023-09-01 | 13051996 | 4502914299 | 10 | TABLERO DE DISTRIBUCION COMEDOR CORTADER | 1 | 3379.98 | 3379.98 | 1 | 2023-10-24 |  | NO RECEPCIONADO | SERVICIOS GENERALES GHERCOR EIRL
CLAURA | 2023-09-02 | 13054575 | 4502921043 | 10 | APLICADOR HDM 500 P/RESINA EPOXICA | 2 | 225.89 | 451.78 | 0 | 2023-10-19 |  | HAGEMSA MOQUEGUA | SERVICIOS GENERALES GHERCOR EIRL
CLAURA | 2023-09-03 | 13054575 | 4502921043 | 20 | LINEA RETRACTIL CABLE DE ACERO 4.8MMX6M | 4 | 195.01 | 780.04 | 0 | 2023-09-26 | 2023-10-09 | WAREHOUSE | SERVICIOS GENERALES GHERCOR EIRL
CLAURA | 2023-09-04 | 13054575 | 4502921043 | 30 | BROCA P/CONCRETO DE 3/4" | 4 | 6.8 | 27.2 | 0 | 2023-09-26 | 2023-10-09 | WAREHOUSE | SERVICIOS GENERALES GHERCOR EIRL
CLAURA | 2023-09-05 | 13054575 | 4502921043 | 40 | CABLE ACERADO P/LINEA DE VIDA DE 5/8" | 2049 | 3.87 | 7929.63 | 0 | 2023-09-26 | 2023-10-09 | WAREHOUSE | SERVICIOS GENERALES GHERCOR EIRL
CLAURA | 2023-09-06 | 13054575 | 4502921043 | 50 | CANDADO P/CABLE DE ACERO DE 5/8" CROSBY | 78 | 2.61 | 203.58 | 0 | 2023-09-26 | 2023-10-09 | WAREHOUSE | SERVICIOS GENERALES GHERCOR EIRL
CLAURA | 2023-09-07 | 13054575 | 4502921043 | 60 | CIZALLA MANUAL DE 24" | 5 | 25.78 | 128.9 | 0 | 2023-09-26 | 2023-10-09 | WAREHOUSE | SERVICIOS GENERALES GHERCOR EIRL
CLAURA | 2023-09-08 | 13054575 | 4502921043 | 70 | COMBO 12 LBS MANGO DE FIBRA | 2 | 27.14 | 54.28 | 0 | 2023-09-26 | 2023-10-09 | WAREHOUSE | SERVICIOS GENERALES GHERCOR EIRL
CLAURA | 2023-09-09 | 13054575 | 4502921043 | 80 | RESINA DE ANCLAJE HIT- RE 500 V3 DE 500 | 40 | 69.37 | 2774.8 | 0 | 2023-10-19 |  | HAGEMSA MOQUEGUA | SERVICIOS GENERALES GHERCOR EIRL
CLAURA | 2023-09-10 | 13054575 | 4502921043 | 90 | SOGA DRIZA 5/8" | 200 | 2 | 400 | 0 | 2023-09-26 | 2023-10-09 | WAREHOUSE | SERVICIOS GENERALES GHERCOR EIRL
MFALCON | 2023-09-11 | 12967626 | 4502924772 | 10 | 20” CLARKSON KNIFE GATE VALVE | 4 | 16683 | 66732 | 4 | 2024-01-09 |  | NO RECEPCIONADO | EMERSON PROC. MANAG. PERU SAC
MFALCON | 2023-09-12 | 12810246 | 4502928314 | 10 | EQUIPO PANDA 4 | 1 | 16887 | 16887 | 0 | 2023-10-16 |  | HAGEMSA LIMA | MAQUINARIAS Y EQUIPOS CURACAUTÍN SP
MFALCON | 2023-09-13 | 12981582 | 4502930636 | 10 | TAMICES 12" DIAMETRO MALLA 200 SETIEMBRE | 2 | 257.31 | 514.62 | 2 | 2023-10-19 |  | NO RECEPCIONADO | DAKER SAC
MFALCON | 2023-09-14 | 12981582 | 4502930700 | 10 | TAMICES 12" DIAMETRO MALLA 200 NOVIEMBRE | 2 | 260.55 | 521.1 | 0 | 2023-09-27 |  | HAGEMSA MOQUEGUA | SERVICIOS GENERALES GHERCOR EIRL
JAGUILAR | 2023-09-15 | 13081472 | 4502931102 | 10 | BARRETA HEX. BAP-175 X 1 1/4" X 1.75 MTR | 5 | 31.79 | 158.95 | 0 | 2023-10-19 | 2023-10-08 | WAREHOUSE | ELECTRO FERRO CENTRO SAC - EFC SAC
JAGUILAR | 2023-09-16 | 13081472 | 4502931102 | 20 | ESCOBILLA P/TAMIZ FINA GILSON TSA-172 | 10 | 15.48 | 154.8 | 10 | 2023-11-11 |  | NO RECEPCIONADO | ELECTRO FERRO CENTRO SAC - EFC SAC
JAGUILAR | 2023-09-17 | 13081472 | 4502931102 | 30 | BROCHA FINE SIEVE, P/LIMPIEZA DE TAMICES | 15 | 33.72 | 505.8 | 15 | 2023-11-11 |  | NO RECEPCIONADO | ELECTRO FERRO CENTRO SAC - EFC SAC
JAGUILAR | 2023-09-18 | 13081472 | 4502931102 | 40 | SMALL FINE SIEVE BRUSH GILSON TSA-168 | 10 | 18.18 | 181.8 | 10 | 2023-11-11 |  | NO RECEPCIONADO | ELECTRO FERRO CENTRO SAC - EFC SAC
JAGUILAR | 2023-09-19 | 13081472 | 4502931102 | 50 | SCRUB BRUSH, 8IN GILSON TSA-232 | 10 | 22.65 | 226.5 | 10 | 2023-11-11 |  | NO RECEPCIONADO | ELECTRO FERRO CENTRO SAC - EFC SAC
JAGUILAR | 2023-09-20 | 13081472 | 4502931102 | 60 | CEMENT/SOIL STEEL WIRE BRUSH GILSON TSA | 20 | 56.13 | 1122.6 | 20 | 2023-11-11 |  | NO RECEPCIONADO | ELECTRO FERRO CENTRO SAC - EFC SAC
JAGUILAR | 2023-09-21 | 13081472 | 4502931102 | 70 | BADILEJO PLANCHA D/BATIR 9" PRETUL 21049 | 5 | 3 | 15 | 0 | 2023-10-03 | 2023-10-07 | WAREHOUSE | ELECTRO FERRO CENTRO SAC - EFC SAC
JAGUILAR | 2023-09-22 | 13081472 | 4502931102 | 80 | MORTAR TROWEL GILSON HMA-306 | 5 | 16.53 | 82.65 | 5 | 2023-11-11 |  | NO RECEPCIONADO | ELECTRO FERRO CENTRO SAC - EFC SAC
JAGUILAR | 2023-09-23 | 13081472 | 4502931102 | 90 | SPOON, STAINLESS STEEL 11.5" LONG GILSON | 10 | 14.62 | 146.2 | 10 | 2023-11-11 |  | NO RECEPCIONADO | ELECTRO FERRO CENTRO SAC - EFC SAC
JAGUILAR | 2023-09-24 | 13081472 | 4502931102 | 100 | CINCEL GRIP 3/4" X 12" C-3/4X12G TRUPER | 10 | 3.84 | 38.4 | 0 | 2023-10-03 | 2023-10-07 | WAREHOUSE | ELECTRO FERRO CENTRO SAC - EFC SAC
JAGUILAR | 2023-09-25 | 13081472 | 4502931102 | 110 | 12" SIEVE, B/S, FULL HT, #200 W/BACKUP | 8 | 246.73 | 1973.84 | 8 | 2023-11-11 |  | NO RECEPCIONADO | ELECTRO FERRO CENTRO SAC - EFC SAC
JAGUILAR | 2023-09-26 | 13081472 | 4502931102 | 120 | 8" SIEVE, S/S, FULL HT, #200 GILSON V8SF | 4 | 130.79 | 523.16 | 4 | 2023-11-11 |  | NO RECEPCIONADO | ELECTRO FERRO CENTRO SAC - EFC SAC
JAGUILAR | 2023-09-27 | 13081472 | 4502931102 | 130 | 8" SIEVE, S/S, FULL HT, #400 GILSON V8SF | 3 | 248.1 | 744.3 | 3 | 2023-11-11 |  | NO RECEPCIONADO | ELECTRO FERRO CENTRO SAC - EFC SAC
JAGUILAR | 2023-09-28 | 13081472 | 4502931102 | 140 | 12" SIEVE, B/S, FULL HT, #400 W/BACKUP | 3 | 393.37 | 1180.11 | 3 | 2023-11-11 |  | NO RECEPCIONADO | ELECTRO FERRO CENTRO SAC - EFC SAC
JAGUILAR | 2023-09-29 | 13081472 | 4502931102 | 150 | EQUIPO P/ DENSIDAD FRASCO, CONO 6 1/2 | 1 | 216.65 | 216.65 | 0 | 2023-10-03 | 2023-10-07 | WAREHOUSE | ELECTRO FERRO CENTRO SAC - EFC SAC
JAGUILAR | 2023-09-30 | 13081472 | 4502931102 | 160 | JGO TERMOHIGOMETRO DIGITAL C/CALIBRACION | 1 | 90.48 | 90.48 | 0 | 2023-10-19 | 2023-10-15 | WAREHOUSE | ELECTRO FERRO CENTRO SAC - EFC SAC
MFALCON | 2023-10-01 | 12981582 | 4502932196 | 10 | AUTOTRANSFORMADOR DE 220 A 110 / POTENCI | 1 | 345.53 | 345.53 | 0 | 2023-10-05 |  | HAGEMSA MOQUEGUA | DAKER SAC
MFALCON | 2023-10-02 | 12981582 | 4502932196 | 20 | TOMACORRIENTE VISIBLE 16A, 2P+T 250 VA | 1 | 14.73 | 14.73 | 0 | 2023-10-05 |  | HAGEMSA MOQUEGUA | DAKER SAC
MFALCON | 2023-10-03 | 12981582 | 4502932196 | 30 | ENCHUFE MENNEKE AÉREO 2P+T 16A | 1 | 20.55 | 20.55 | 0 | 2023-10-05 |  | HAGEMSA MOQUEGUA | DAKER SAC
MFALCON | 2023-10-04 | 12981582 | 4502935608 | 10 | ABRAZADERAS TRELLEX DE 6" | 12 | 149.32 | 1791.84 | 0 | 2023-10-05 |  | NO RECEPCIONADO | WONG Y COMPLEMENTOS INDUSTRIALES
MFALCON | 2023-10-05 | 12970524 | 4502936334 | 10 | MOTOBOMBAS + ACCESORIOS | 2 | 6150 | 12300 | 2 | 2023-10-21 |  | NO RECEPCIONADO | MASTERFLOW S.A.C.
CLAURA | 2023-10-06 | 13084097 | 4502936341 | 10 | GLOW PLUG LIGHT MDA50/121 | 1 | 75 | 75 | 1 | 2023-10-23 |  | NO RECEPCIONADO | THIESSEN DEL PERU S.A.
CLAURA | 2023-10-07 | 13084097 | 4502936341 | 20 | GAUGE / MANÓMETRO | 1 | 128.24 | 128.24 | 1 | 2023-10-23 |  | NO RECEPCIONADO | THIESSEN DEL PERU S.A.
CLAURA | 2023-10-08 | 13084097 | 4502936341 | 30 | FACER BLADE SET | 1 | 494.12 | 494.12 | 1 | 2023-10-23 |  | NO RECEPCIONADO | THIESSEN DEL PERU S.A.
CLAURA | 2023-10-09 | 13084097 | 4502936341 | 40 | OIL FILTER / FILTRO DE ACEITE HIDRÁULICO | 1 | 58.46 | 58.46 | 1 | 2023-10-23 |  | NO RECEPCIONADO | THIESSEN DEL PERU S.A.
CLAURA | 2023-10-10 | 13084097 | 4502936341 | 50 | IN-LINE FUEL FILTER DIESEL | 1 | 28 | 28 | 1 | 2023-10-23 |  | NO RECEPCIONADO | THIESSEN DEL PERU S.A.
CLAURA | 2023-10-11 | 13084097 | 4502936341 | 60 | FUEL PUMP MOD ASSY | 1 | 365 | 365 | 1 | 2023-10-23 |  | NO RECEPCIONADO | THIESSEN DEL PERU S.A.
CLAURA | 2023-10-12 | 13084097 | 4502936341 | 70 | MANÓMETRO | 1 | 55 | 55 | 1 | 2023-10-23 |  | NO RECEPCIONADO | THIESSEN DEL PERU S.A.
CLAURA | 2023-10-13 | 13084097 | 4502936341 | 80 | 3000PSI PRESSURE GAUGE | 1 | 152.94 | 152.94 | 1 | 2023-10-23 |  | NO RECEPCIONADO | THIESSEN DEL PERU S.A.
CLAURA | 2023-10-14 | 13084097 | 4502936341 | 90 | OIL HYD RANDO HDZ 46 (BALDE) DE 5 GALONE | 2 | 185 | 370 | 2 | 2023-10-23 |  | NO RECEPCIONADO | THIESSEN DEL PERU S.A.
CLAURA | 2023-10-15 | 13084097 | 4502936341 | 100 | OIL_SAE 15W-40 - GALÓN | 3 | 54 | 162 | 3 | 2023-10-23 |  | NO RECEPCIONADO | THIESSEN DEL PERU S.A.
CLAURA | 2023-10-16 | 13084097 | 4502936341 | 110 | OIL FILTER FOR MDA00121 | 1 | 35.34 | 35.34 | 1 | 2023-10-23 |  | NO RECEPCIONADO | THIESSEN DEL PERU S.A.
CLAURA | 2023-10-17 | 13084097 | 4502936341 | 120 | F31 AIR CLEANER KIT FOR MDA121 | 1 | 764.71 | 764.71 | 1 | 2023-10-23 |  | NO RECEPCIONADO | THIESSEN DEL PERU S.A.
CLAURA | 2023-10-18 | 13084097 | 4502936341 | 130 | AIR CLEANER CANISTER & FILTER | 1 | 650 | 650 | 1 | 2023-10-23 |  | NO RECEPCIONADO | THIESSEN DEL PERU S.A.
CLAURA | 2023-10-19 | 13084097 | 4502936341 | 140 | 2.5LG,150-650DEG F TERMÓMETRO | 1 | 58 | 58 | 1 | 2023-10-23 |  | NO RECEPCIONADO | THIESSEN DEL PERU S.A.
CLAURA | 2023-10-20 | 13084097 | 4502936341 | 150 | SET 6 UNIDADES | 1 | 360 | 360 | 1 | 2023-10-23 |  | NO RECEPCIONADO | THIESSEN DEL PERU S.A.
MFALCON | 2023-10-21 | 12981582 | 4502936356 | 10 | ESMERIL ANGULAR 4.5" 1250 W 220V MILWAUK | 4 | 133.27 | 533.08 | 4 | 2023-10-19 |  | NO RECEPCIONADO | SERVICIOS GENERALES GHERCOR EIRL
MFALCON | 2023-10-22 | 12981582 | 4502936356 | 20 | LLAVE DE IMPACTO INALAMBRICA 1/2" 780 LB | 4 | 1398.06 | 5592.24 | 4 | 2023-10-19 |  | NO RECEPCIONADO | SERVICIOS GENERALES GHERCOR EIRL
MFALCON | 2023-10-23 | 12981582 | 4502936356 | 30 | TALADRO INALAMBRICO 1/2" 18V SNAPON | 4 | 863.44 | 3453.76 | 4 | 2023-10-19 |  | NO RECEPCIONADO | SERVICIOS GENERALES GHERCOR EIRL
MFALCON | 2023-10-24 | 12970524 | 4502960310 | 10 | BRIDA VITAULICA DE 6" | 40 | 260.83 | 10433.2 | 0 | 2023-10-14 | 2023-10-18 | HAGEMSA LIMA | THIESSEN DEL PERU S.A.
MFALCON | 2023-10-25 | 12970524 | 4502960310 | 20 | ACOPLE FLEXIBLE DE 6" | 20 | 103.7 | 2074 | 0 | 2023-10-14 | 2023-10-18 | HAGEMSA LIMA | THIESSEN DEL PERU S.A.
MFALCON | 2023-10-26 | 12967626 | 4502909729 | 10 | FLOTADORES DE 20" | 32 | 910 | 29120 | 32 | 2023-10-24 |  | NO RECEPCIONADO | ITO SUPPLIES & SERVICES S.A.C.
MFALCON | 2023-10-27 | 12967626 | 4502882550 | 10 | FLOTADOR BIPARTIDO ID-407 (16") | 213 | 500 | 106500 | 213 | 2023-11-13 | 2023-10-18 | HAGEMSA LIMA | ITO SUPPLIES & SERVICES S.A.C.
Note on L30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PROCESO DE RECEPCIÓN EN HAGEMSA
Note on L37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PROCESO DE RECEPCIÓN EN HAGEMSA

## Data (hidden)
JAGUILAR | NO RECEPCIONADO
MFALCON | HAGEMSA LIMA
DQUIÑONE | HAGEMSA MOQUEGUA
WAREHOUSE
DM5
DM8
PLATAFORMA J

## Pendientes aprobación (hidden)
2023-10-03 | PR | DESCRIPCIÓN | PENDIENTE DE APROVAR
| 13102339 | SPOOL RECTO 30" | JUSTO ENRIQUEZ SERRRANO
SPOOL RECTO 30"
SPOOL RECTO 20"
SPOOL RECTO 20"
GEOTEXTIL 250 G-M2
MANGUERA KANALEX DE 6"
ACOPLES RAPIDOS DE 6" (HEMBRA Y MACHO)
MANGUERA KANALEX DE 8"
ACOPLES RAPIDOS DE 8" (HEMBRA Y MACHO)
| 13096104 | ASISTENCIA TÉCNICA ANUAL SONARTRAC | JUSTO ENRIQUEZ SERRRANO

## Hoja2 (hidden)
#VALUE! | #VALUE!